## Sheet1
Week | 9/25-10/2 | 10/2-10/9 | 10/9-10/16 | 10/16-10/23 | 10/23-10/30 | 10/30-11/6 | 11/6-11/13 | 11/13-11/20 | 11/20-11/27 | 11/27-12/4 | 12/4-12/11 | 12/11-12/18 | 12/18-12/25 | 12/25-1/1 | 1/8-1/15 (Beginning of Quarter 2) | 1/15-1/22 | 1/22-1/29 | 1/29-2/5 | 2/5-2/12 | 2/12-2/19 | 2/19-2/26 | 2/26-3/4 | 3/4-3/11 | 3/11-3/18 | 3/18-3/25 | END OF TERM
Task 1 | Topic Decision | Data Discovery | Download/Configure Splunk for imported logs | Test Splunk Signature Based Rules | Set up design for ML (DT, Linear Model?) | Compare results of different simple ML models and select best one/combination | Use data with ML to make baseline for model | Test ML ability to correctly categorize data | Tweak model as needed for accuracy |  |  | Winter break | Winter break | Winter break | Figure out how to visualize data | Visualize data via some external plugin | Develop easily readable explanations per result | Test results with audience to see if truly explainable | Tweak explanation generator according to testing | Finalize report for submission
Task 2 | Studying Overview of IDS's | Schedule Building |  | Be able to indicate which rule alerted for each alert | [10 empty] | (heatmap, network graph, time leading up to alert, etc. |  |  |  |  | If extra time, upgrade ML model to improve accuracy